## Executive Summary
SherryJo Calendar App - Cloudflare Migration Charter Status
Evidence-based assessment as of 2026-08-01 ¦ Single repository ¦ Free-tier objective
Current architecture | Cloudflare Worker edge proxy -> Render FastAPI origin -> Supabase PostgreSQL, plus native /api/platform/status
Current migration position | Phase 2 shadow parity complete; first stateless Worker-native application route is live; OAuth/canary gates remain
Cloudflare-primary execution | Early (estimated 16%): one stateless native route; no Worker-native auth, business data reads/writes, jobs, or WebSockets
Foundation/readiness | Strong (estimated 80%): architecture, contracts, proxy, native route, live parity, rollback drill, CI checks, and runbooks exist
Overall charter estimate | Approximately 32% complete using weighted milestone scoring; this is not a claim of production cutover
Live Cloudflare edge | https://sherryjo-calendar-edge.realty-cal.workers.dev/__edge/health - verified status=ok
Live proxied application | https://sherryjo-calendar-edge.realty-cal.workers.dev/health - verified status=ok, schema_status=ok
Committed/live SHA | 135dccf8d6c2f980348166610a4482d1843e21af (local HEAD and live Render at audit time)
Important deployment state | Migration and Admin changes remain uncommitted; Worker version be60f8d2-ea34-4739-82ed-0eef699f80a5 is live from local source
Next decision gate | Register Worker OAuth callbacks and update Render BASE_URL; then create behavior fixtures and a least-privilege Supabase gateway
What is operational now |  | What is not operational yet
YES | Render FastAPI verified locally and at its direct deployment | LIMITED | Only /api/platform/status executes natively; FastAPI business routes remain on Render
YES | Supabase remains authoritative | NO | No Worker-native authentication or OAuth
YES | Cloudflare workers.dev edge URL is live | NO | No Worker-native authenticated database reads/writes
YES | Worker proxies HTTP and rewrites origin redirects | NO | No D1/KV/R2/DO/Queues production usage
YES | Edge health, proxied health, native status, and the 16/16 live gate pass | NO | No independent Cloudflare failover if Render fails
YES | Worker tests 5/5, Wrangler dry-run, deployment contract, live gate, and local/direct Render checks pass | NO | Render is origin, not a true hot spare yet

## Phase Roadmap
Phase | Milestone | Status | Estimated % | Evidence / Current Result | Gate Remaining | Recommended Next Action
0 | Safety foundation and reversible edge proxy | Complete | 98 | Proxy, native status route, redirects, contracts, and timed rollback/restore drill; Render retained | Commit reviewed changes and preserve the verified rollback path | Commit/push only after final migration review
1 | Baseline inventory and production fingerprints | Partial | 80 | Architecture/env/Alembic, local/direct Render fingerprints, dated shadow evidence, and authenticated operator evidence archived | Archive Supabase row counts and scheduler baseline | Complete the production fingerprint evidence pack
2 | workers.dev shadow parity validation | Complete | 100 | Automated live gate 16/16; authenticated reads, reversible writes, upload, OAuth rejection and WebSocket echo pass | Gate passed; retain evidence after every Worker deployment | Proceed to OAuth and operator-canary prerequisites
3 | Operator-only canary | Partial | 20 | Authenticated operator exercised workers.dev and Worker rollback/restore passed; no dedicated canary hostname or observation window | Worker OAuth callback registration, BASE_URL cutover, thresholds, seven-day observation | Register callbacks, redeploy Render, and begin observation
4 | Cloudflare edge becomes primary route | Not Started | 0 | No production DNS/custom-domain cutover | Rollback drill, origin monitoring, OAuth validation | Prepare custom domain and rehearsed rollback
5 | Clean architecture/shared behavior contracts | Partial | 10 | Native route ownership boundary exists; business services remain ORM/framework coupled | Extract a read use-case contract and shared fixture corpus | Pilot one read-only calendar behavior contract
6 | Worker-native authenticated reads | Not Started | 5 | One unauthenticated stateless route is native; authenticated reads still proxy | Auth bridge, least-privilege Supabase gateway, RLS layer 2, response parity | Begin only after behavior and security contracts pass
7 | Queues/Cron idempotent async work | Not Started | 0 | APScheduler remains in Render | Idempotency keys, replay tests, provider-write dedupe | Design queue operation identity before binding resources
8 | D1 rebuildable read-model evaluation | Not Started | 0 | No D1 binding or schema | Schema mapping, sync, reconciliation, restore drill, free-tier fit | Keep Supabase authoritative; write D1 decision record
9 | Worker-native writes and full autonomy | Blocked | 0 | No Worker-native writes or outbox | Transactional outbox, conflict resolution, route canary, zero divergence | Blocked until Phases 5-8 gates pass
10 | Render validated as true hot spare | Blocked | 0 | Render is currently active origin | Cloudflare-independent runtime plus tested failback/failover | Define RTO/RPO and automate failover drills

## Charter Checklist
ID | Charter Requirement | Status | Estimated % | Evidence | What Exists | What Remains | Risk | Next Action
1 | Current-state architecture assessment | Complete | 90 | docs/architecture/dual_platform_modernization.md | Presentation, application, domain, persistence, auth, real-time and operational risks assessed | Add measured production baseline snapshot | Low | Maintain assessment at each gate
2 | Target architecture and diagrams | Complete | 90 | docs/architecture/dual_platform_modernization.md | Target Mermaid diagram and phased execution model documented | Add current deployed-state diagram and ownership labels | Low | Add a current-state diagram after commit
3 | Complete target file structure | Partial | 35 | docs/architecture/dual_platform_modernization.md; platform/cloudflare/; deployment/ | Proposed clean structure and platform folders exist | core/, adapters/, api/worker_routes and contract/failover test folders not implemented | Medium | Introduce incrementally by use case
4 | Production-ready Cloudflare Worker entrypoint | Complete | 95 | platform/cloudflare/src/worker.js; platform/cloudflare/test/worker.test.js; artifacts/cloudflare-shadow-parity-2026-08-01.json | Proxy safeguards plus first native route; Worker tests 5/5 and live gate 16/16 | Automate the live gate in hosted CI | Low | Retain post-deploy smoke and rollback evidence
5 | Render deployment remains functional | Complete | 98 | render.yaml; run.py; live /health and /health/schema; artifacts/cloudflare-shadow-parity-2026-08-01.md | Canonical local FastAPI and direct Render health/schema/auth rejection/OpenAPI/WebSocket checks pass | Deploy the uncommitted Admin changes and repeat the same checks | Low | Retain local/direct Render verification after every Render release
6 | Cloudflare as strategic primary platform | Partial | 20 | workers.dev edge URL; live /api/platform/status | Cloudflare owns edge routing and one stateless application route | All authenticated business execution remains on Render | High | Do not reclassify Cloudflare as primary runtime yet
7 | Render as continuously ready hot spare | Partial | 20 | Render origin plus independent Worker-native status route | Render remains healthy and deployable; one route no longer depends on it | Cloudflare cannot serve business workflows during Render failure | Critical | Expand independence only behind contract and security gates
8 | Single Git repository supports both targets | Partial | 70 | wrangler.toml; render.yaml; platform/; deployment/ | Both target configs are in one working tree | Migration files are uncommitted; no dual release orchestration | High | Commit foundation and add release workflow
9 | Platform-specific logic isolated | Partial | 55 | platform/cloudflare/; deployment/platform_contract.py | Cloudflare proxy and deployment validation are isolated | FastAPI services still mix domain, ORM and framework concerns | Medium | Extract one port/use case at a time
10 | Business logic platform agnostic | Not Started | 10 | app/services/ | Existing service behavior can seed contracts | Services depend on SQLAlchemy/FastAPI and cannot run in Workers | High | Create platform-neutral behavior fixtures
11 | Authentication parity on both platforms | Partial | 45 | artifacts/cloudflare-shadow-parity-2026-08-01.md; deployment/shadow_parity.py | Cloudflare forwards auth correctly; authenticated reads, reversible database access, and WebSocket echo pass through the edge | No Worker-native JWT validation, OAuth authority, or provider callback cutover | Critical | Register Worker callbacks and define the native auth contract before authenticated native routes
12 | Database schema portability | Not Started | 15 | alembic/; app/models.py | PostgreSQL schema is migration-controlled | No D1 mapping, SQLite compatibility rules, reconciliation or restore process | High | Write D1 feasibility/portability decision record
13 | Environment variable inventory and compatibility | Complete | 90 | deployment/platform_contract.py; docs/operations/dual_platform_runbook.md | Required Render and edge variables validated/documented | Add future bindings only when introduced | Low | Keep contract synchronized with configs
14 | Secrets management strategy | Partial | 70 | render.yaml; docs/operations/dual_platform_runbook.md | Render secrets externalized; Worker currently has no secrets; policy documented | No rotation drill or Worker-native secret inventory | Medium | Add rotation evidence before native auth
15 | CI unit/integration tests | Complete | 85 | .github/workflows/tests.yml; app/tests/ | Pytest runs with PostgreSQL service | Workflow changes are uncommitted; optional live Supabase E2E remains opt-in | Medium | Commit workflow and verify GitHub run
16 | Cloudflare deployment readiness gate | Complete | 95 | .github/workflows/tests.yml; platform/cloudflare/test/; deployment/shadow_parity.py | Worker tests, dry-run, live native ownership and 16-check post-deploy gate exist | Run the live gate automatically in hosted CI | Low | Add a credential-safe hosted smoke job
17 | Render deployment readiness gate | Partial | 65 | .github/workflows/tests.yml; render.yaml | Python compile, tests, environment contract and migration head checks exist | No automated live Render post-deploy smoke in CI | Medium | Run smoke after each deploy
18 | Cross-platform behavior contract tests | Partial | 25 | deployment/shadow_parity.py; platform/cloudflare/test/worker.test.js | Proxy parity corpus and explicit native route ownership contract exist | No shared business behavior fixtures for FastAPI and Worker adapters | High | Create the first read-only behavior fixture corpus
19 | WebSocket parity | Complete | 90 | app/routers/websocket.py; artifacts/cloudflare-shadow-parity-2026-08-01.md | Invalid-token rejection parity and authenticated exact echo pass through both hosts | Add reconnect and sustained-connection coverage before Durable Objects | Low | Retain WebSocket checks in every edge release
20 | End-to-end deployment tests | Partial | 75 | deployment/shadow_parity.py; artifacts/cloudflare-shadow-parity-2026-08-01.json; authenticated operator evidence | Automated 16-check live gate plus authenticated reads, write cleanup, upload and WebSocket checks | Authenticated flow is operator-run rather than hosted CI | Medium | Add credential-safe hosted smoke coverage
21 | Failover tests and operational drill | Partial | 55 | docs/operations/dual_platform_runbook.md; artifacts/cloudflare-shadow-parity-2026-08-01.md | Worker rollback completed in 58.45 seconds and restore in 4.22 seconds with auth, database reads, and WebSocket echo available | DNS/edge bypass drill, measured full RTO/RPO, and origin-independent business runtime remain | High | Run a full edge bypass and restore drill during an approved window
22 | Rollback strategy | Partial | 90 | docs/operations/dual_platform_runbook.md; artifacts/cloudflare-shadow-parity-2026-08-01.md | Exact Worker rollback and restore were executed, timed, validated, and returned the native version to 100% traffic | Later native-write/data rollback and DNS bypass procedures remain untested | Medium | Retain this drill and execute full edge bypass before primary cutover
23 | Cost analysis/free-tier objective | Partial | 65 | docs/architecture/dual_platform_modernization.md | Roles and cost pressure identified by service | No current quotas/dashboard usage or capacity model | Medium | Capture monthly usage and phase budgets
24 | Security assessment | Partial | 70 | docs/security/production_runbook.md; app/db_security.py; app/utils/crypto.py | RLS layer 1 and OAuth token encryption exist; debt identified | RLS layer 2, asymmetric JWT strategy, WS token hardening and rotation drills | High | Complete threat model before direct DB access
25 | Scalability/high availability analysis | Partial | 55 | docs/architecture/dual_platform_modernization.md | Free-tier constraints and optimization direction documented | No measured load, multi-region design, SLOs or capacity thresholds | Medium | Define SLOs and run load baseline
26 | D1 integration | Not Started | 0 | wrangler.toml | Correctly absent during proxy phase | All design, bindings, migrations, sync and reconciliation work remains | High | Evaluate only as rebuildable read model first
27 | KV integration | Not Started | 0 | docs/architecture/dual_platform_modernization.md | Non-authoritative policy documented | No binding or measured use case | Low | Defer until a disposable-cache need is proven
28 | R2 integration | Not Started | 0 | docs/architecture/dual_platform_modernization.md | Correctly deemed unnecessary currently | No user-binary storage requirement | Low | Do not add without a product need
29 | Durable Objects integration | Not Started | 0 | docs/architecture/dual_platform_modernization.md | Reserved for later WebSocket proof | No coordinator, storage or tests | Medium | Evaluate after WS contract baseline
30 | Queues/Cron integration | Not Started | 0 | app/services/sync_scheduler.py | Render APScheduler performs jobs | No idempotency/replay design or bindings | High | Design dedupe before migration
31 | Admin dual-platform visibility and controls | Partial | 80 | app/routers/admin.py; app/static/admin.js; app/templates/admin.html | Local changes detect edge route and add guarded repository controls | Changes are not committed/deployed; desktop process launch cannot work from cloud runtime | Medium | Commit, deploy, then validate labels through workers.dev
32 | Production cutover with zero disruption | Not Started | 0 | N/A | No production cutover attempted, preserving current users | Canary, monitoring, rollback drill and native capability remain | Critical | Do not cut over until gates pass

## Environment Matrix
Variable / Binding | Render/FastAPI | Cloudflare Now | Cloudflare Future | Status / Rule
ADMIN_SETUP_CODE | Required secret | Not copied | Only if Worker owns admin registration | Preserve on auth authority
BASE_URL | Public URL/callback authority | N/A | Cloudflare custom domain after cutover | Must be HTTPS
DATABASE_URL | Supabase PostgreSQL secret | Not copied | Gateway/Hyperdrive decision required | Never expose to browser
DB_TYPE | postgres | N/A | N/A | Production must fail closed
DISABLE_SQLITE_FALLBACK | Enabled | N/A | N/A | Required in production
GOOGLE_CLIENT_ID/SECRET/REDIRECT | Required | Forwarded to Render | Worker-native auth requires secure secrets and callback parity | Register canary URL before testing
MS_CLIENT_ID/SECRET/TENANT/REDIRECT | Required | Forwarded to Render | Worker-native auth requires secure secrets and callback parity | Register canary URL before testing
JWT_ALGORITHM/JWT_SECRET_KEY | HS256 authority | Not copied | Requires coordinated parity/rotation strategy | Do not fork token semantics
REQUIRE_DB_KIND | postgres | N/A | N/A | Production guardrail
TOKEN_ENCRYPTION_KEY | Required secret | Not copied | Only needed if Worker handles provider credentials | Never commit
ORIGIN_BASE_URL | N/A | Render HTTPS origin | Removed only after independent Worker app exists | Current edge proxy dependency
D1/KV/R2/DO/Queues bindings | N/A | None | Introduce per approved phase gate | No speculative resources

## Risks and Next Actions
Priority | Risk / Gap | Impact | Dependency | Recommended Action | Gate / Exit Evidence | Owner Role
P0 | Migration foundation is uncommitted | Live Render/Admin cannot reflect audited changes | Final review and commit workflow | Commit and push current migration files as one reviewed foundation change | GitHub CI green; Render and Worker smoke green | DevOps
P0 | Cloudflare business routes still proxy to Render | Render outage still takes down user workflows | Worker-native behavior, auth and data contracts | Keep runtime claims explicit and migrate only gated read routes | First domain fixture and secure read gateway pass | Architecture
P1 | No full edge bypass/failover drill | Worker version rollback is proven, but complete route bypass timing remains unknown | Approved maintenance window and stable origin | Run DNS/edge bypass and restore drill without changing database authority | Measured full RTO/RPO with health, auth, calendar and WebSocket checks | SRE
P0 | No shared business behavior fixtures | Future native business routes may silently diverge | Domain contract design | Create fixtures before the first Worker-native business route | FastAPI and Worker adapters pass identical fixtures | QA/Architecture
P2 | WebSocket parity regression | A later edge change could break upgrades or authenticated echo | Live shadow URL and operator session | Retain invalid-token and valid-echo checks in every release | Automated rejection plus recorded authenticated echo pass | Full Stack
P1 | OAuth callbacks still target Render | Worker hostname cannot become canonical OAuth origin | Google/Microsoft console access and Render BASE_URL | Register Worker callbacks, update BASE_URL, redeploy and reconnect both providers | Google and Microsoft successful callback evidence | Security
P1 | Business logic coupled to ORM/framework | Cannot execute in Workers | Incremental ports strategy | Extract one read use case and behavior contract | FastAPI unchanged; Worker fixture parity | Software
P1 | No RLS layer 2/direct Worker DB design | Direct database access could bypass tenant isolation | Supabase role and gateway choice | Threat-model and implement least-privilege gateway | Tenant isolation integration tests | Security/DB
P2 | D1 portability unknown | Schema/data divergence risk | Contract and read gateway | Document schema mapping and read-model reconciliation | Restore/reconcile drill passes | Database
P2 | Async jobs lack replay identity | Duplicate provider calendar writes | Operation ID design | Add idempotency keys before Queues | Duplicate delivery test writes once | Systems
P2 | Free-tier capacity is unmeasured | Unexpected sleep/quota/egress failures | Vendor usage data | Capture quotas, current usage and alert thresholds | Monthly capacity worksheet updated | FinOps/SRE

## Evidence Index
Evidence | Purpose | Audit Finding
wrangler.toml | Cloudflare Worker configuration | workers_dev enabled; Render origin configured; no database or auth bindings
platform/cloudflare/src/worker.js | Edge implementation | Stateless reverse proxy plus native /api/platform/status route
platform/cloudflare/test/worker.test.js | Worker unit tests | Five tests cover native ownership, proxy, redirects and failure behavior
render.yaml | Render deployment blueprint | Render remains full FastAPI runtime
deployment/platform_contract.py | Dual-target environment validation | Render and Cloudflare edge contracts defined
.github/workflows/tests.yml | CI readiness gates | PostgreSQL pytest, contract, Worker tests/dry-run and Alembic head
docs/architecture/dual_platform_modernization.md | Architecture and phased plan | Correctly describes Phase 0 edge proxy and future gates
docs/operations/dual_platform_runbook.md | Operations/rollback | Native route inventory, exact rollback procedure and database guardrails documented
docs/security/production_runbook.md | Security operations | RLS and token encryption guidance
app/routers/admin.py | Admin deployment status and controls | Platform-aware changes exist locally but are uncommitted
Live /__edge/health | Cloudflare edge health | Verified 2026-08-01: status ok, mode render-origin-proxy
Live /health through workers.dev | End-to-end proxy health | Verified 2026-08-01: app running, schema ok
Git HEAD 135dccf8d6c2 | Committed/live baseline | Matches live Render; migration changes remain working-tree only
deployment/shadow_parity.py | Repeatable live release gate | 16/16 checks include proxy parity, OAuth rejection, WebSocket rejection and native route ownership
artifacts/cloudflare-shadow-parity-2026-08-01.json | Machine-readable live evidence | Passed 16 of 16 after Worker-native deployment
artifacts/cloudflare-shadow-parity-2026-08-01.md | Authenticated and operational evidence | Reads, reversible writes, multipart upload and valid WebSocket echo pass; OAuth cutover blocker recorded
Live /api/platform/status | First Worker-native application route | Verified 2026-08-01: 200, no-store, platform cloudflare-worker, mode worker-native; version be60f8d2-ea34-4739-82ed-0eef699f80a5
2026-08-01 Worker rollback/restore drill | Executed rollback behavior evidence | Rollback 58.45s; restore 4.22s; proxy auth/database/WebSocket stayed healthy; restored gate 16/16 and native database cleanup passed
2026-08-01 local and direct Render verification | Render runtime continuity evidence | Local and deployed health/schema/auth rejection/OpenAPI/WebSocket checks pass; schema equal except timestamp; only two intentional uncommitted Admin paths differ

## Closure Exceptions
Final Project Closure Exceptions - 2026-08-02
Gate 158 status: BLOCKED. This sheet contains no credential values and supersedes optimistic status claims in earlier tabs.
Charter Steps | Stage | Closure Status | Blocker Type | Copilot Work Completed | Distinct Owner / Manual Work Required | Required Exit Evidence | Credential / Token Method | Commit / Push Dependency
5, 9, 11 | A1 | Accepted gap; review open | Owner measurement | Baseline collector, masking tests, provider captures, and live parity evidence exist. | Measure direct Render cold-start latency or explicitly retain the documented exception. | Dated cold-start samples or signed exception in the closure record. | None. | No
17, 19, 20, 22 | A2 | Blocked | Owner security incident response | Threat model, secret inventory, JWT/Fernet rotation tests, WebSocket tickets, Gitleaks CI, and log redaction are implemented. | Rotate/revoke the exposed Supabase credential, decide historical Git response, review residual High/Critical findings, and approve the threat model. | Revocation/rotation timestamp, clean current and historical scans or accepted incident record, production JWT/ticket evidence, signed security review. | Create a Supabase token in Account Preferences > Access Tokens; enter through hidden PowerShell prompt. Never use browser cookies. | Yes; deployed verification needs exact release SHA
26-30, 32 | A3 | Blocked | Owner policy and live canary | Bounded capacity probe, local windows, usage/headroom, provisional thresholds, and overage exception are documented. | Choose best-effort free tier or paid always-on RTO; approve budget/thresholds; measure cold start and authenticated canary latency; resolve or reaccept egress overage. | Signed reliability decision, cold-start samples, canary report, approved budget, current vendor usage. | Smoke token only through environment; provider dashboard access remains owner-controlled. | Yes for canary evidence
39-44 | B1 | Code complete; live gate blocked | Prerequisite security/live database | FastAPI contract, SQLAlchemy adapter, Worker adapter, strict JWT, route ownership modes, and shared fixture tests exist. | Provision least-privilege PostgreSQL/Hyperdrive and public JWT keys; run live PostgreSQL RLS and exact cross-adapter shadow parity. | No skipped required RLS tests, zero unexplained normalized differences, rollback to proxy proven. | Use Wrangler secret prompts and provider-managed database credential; never workbook/chat. | Yes
47-55 | B2 | Blocked | Deployment and GitHub environments | Authenticated reversible harness, cleanup fallback, workflow split, concurrency, and artifact retention are implemented. | Configure protected GitHub environments/secrets, commit and deploy `/ws/ticket`, then run corrected canary and production smoke jobs. | GitHub run URLs, all required jobs pass, cleanup confirmed, intentional broken release blocks promotion. | GitHub environment secrets: SHERRYJO_SMOKE_EMAIL/PASSWORD and scoped Cloudflare token. | Yes; current Render release lacks `/ws/ticket`
56-68 | C | Blocked | Owner hostname/OAuth plus seven elapsed days | Isolated canary config, callback-host validation, observability, monitoring workflow, and smoke automation exist locally. | Choose hostname; create canary; register Google/Microsoft callbacks; configure secrets; verify full manual matrix; operate and record seven consecutive days. | Hidden-secret callback screenshots, seven daily observations, zero elevated alarms, rollback rehearsal. | Cloudflare already OAuth-authenticated locally; provider callback changes require Google/Microsoft dashboard sessions. | Yes; canary must deploy exact SHA
69-82 | D | Blocked | Production traffic change | Proxy/header handling, smoke automation, rollback commands, and runbook are documented. | Verify DNS/certificate/callbacks, approve change window, attach production hostname, run full matrix, time bypass and restore, and approve keeping traffic. | Before/after DNS and route records, exact SHA, complete smoke, independent Render health, timed bypass/restore within selected RTO. | Use Cloudflare OAuth session; no token needed. OAuth provider dashboards remain manual. | Yes
85-95 | E | Blocked | Owner secrets/live Hyperdrive/RLS/canary | JWT verifier and negative tests, read role migration, RLS suite, Hyperdrive adapter, and proxy/shadow/canary/native modes are implemented; deployment is forced to proxy. | Provision public keys and least-privilege role, create cache-disabled Hyperdrive, run PostgreSQL/RLS tests, shadow operator traffic, then staged canary traffic. | Authorization, response, latency, load, RLS, zero-difference shadow, and instant proxy rollback reports. | JWT public keys and database credential through Wrangler/provider prompts only. | Yes
97-106 | F1 | Decision blocked | Owner architecture decision and production volume | All scheduler jobs are inventoried; idempotent prune/rollup behavior is tested; engineering recommendation is defer. | Capture dated production volume and approve defer, Cron only, or Queues + Cron. If migration is selected, authorize ledger and canary work. | Signed decision; for implementation, operation ledger and duplicate/retry/dead-letter proof. | Authenticated admin read token through environment if volume endpoints require it. | Only if implementation selected
110-118 | F2 | Decision blocked | Owner defer/deploy decision | PostgreSQL compatibility inventory, minimal D1 projection, exclusions, reconciliation contract, and defer recommendation are documented. | Approve defer D1, or authorize local migrations/rebuild/reconciliation/capacity implementation after Worker-read gates pass. | Signed decision; if deployed, zero-difference rebuild and capacity report. | No token for defer; Cloudflare OAuth session can manage D1 only after approval. | Only if implementation selected
123-126 | F3 | Decision blocked | Owner binding decisions | KV deferred, R2 not applicable, and Durable Objects deferred with measured revisit triggers. | Approve or reject each recommendation separately. | Signed architecture decision for KV, R2, and Durable Objects. | None. | No
127-138 | G | Blocked; not started | Failed prerequisites and high-risk write authority | Guardrails prohibit Worker writes before read/security/backup/reconciliation gates. | After all prerequisites pass, approve one low-risk command contract, outbox migration, replay consumers, shadow comparison, and operator canary writes. | Atomicity/failure suite, operation audit, zero divergence, Render compatibility, tested rollback. | Future database/write credentials only through provider secret stores. | Yes; multiple reviewed gates required
139-150 | H | Blocked | Owner RTO/backup/change window and Cloudflare autonomy | Independent direct Render synthetic and default-disabled monitor workflow are implemented and tested locally. | Select RTO/RPO, configure monitor secrets, capture verified Supabase recovery point, schedule drill, switch traffic, run matrix, reconcile, and fail back. | Timed failover/failback, complete functional matrix, scheduler ownership, backup reference, zero lost/duplicate writes. | Render monitor secrets in protected GitHub environment; Supabase token via hidden prompt if API evidence is collected. | Yes
151 | Final | Partial | Unavailable live/integration/failover prerequisites | Local Python suite passed 507 with 29 skips; Worker suite passed 27; focused monitor tests passed 10; both Wrangler dry-runs passed. | Run PostgreSQL-required tests, hosted E2E, deployment, security scan, canary load, and failover suites against exact release. | All required suites pass with no required skips and archived reports. | Test-account and provider credentials through protected environments only. | Yes
152 | Final | Blocked | GitHub exact-SHA checks | CI workflows are defined locally. | After final sign-off, commit/push and wait for every required GitHub check on that SHA. | Required checks green for exact release SHA. | No GitHub CLI installed; use approved desktop commit workflow and authenticated GitHub session. | Yes; this is the final approval boundary
153 | Final | Blocked | Undeployed working tree | Current root Worker versions and local Alembic head are inspectable. | Deploy exact SHA to Render and Cloudflare, then verify both identifiers and Supabase migration head. | Cloudflare/Render exact SHA and Alembic k964e55bbb88 recorded together. | Cloudflare needs no new local token; Render API key may be created and entered through hidden prompt. | Yes
154-155 | Final | Partial | Earlier gates incomplete | Architecture, environment matrix, threat model, capacity record, deployment/failover runbook, and closure report are updated for current state. | Approve conditional decisions and complete missing live evidence before marking every workstream Complete/deferred/not applicable. | Reviewed document set and signed decision index. | None. | Yes for final provenance
156 | Final | Owner sign-off required | Owner approval | Residual risks and free-tier limitations are listed in this worksheet and final closure report. | Approve reliability statement, Supabase overage, credential incident response, deferred products, and residual risks. | Dated owner approval with accepted/rejected items. | None. | No
157 | Final | Blocked | Owner change window plus prerequisites | Failover procedure and synthetic checks are documented. | Execute final failover/failback only after backup, exact SHA, autonomy, and RTO/RPO gates pass. | Archived timed drill with reconciliation and zero lost/duplicate writes. | Provider sessions and protected smoke secrets only. | Yes
158 | Final | FAIL / BLOCKED | Cloudflare is not autonomous | Closure assessment is complete and does not claim a false pass. | Cloudflare must independently handle the complete production workload; Render must pass hot-spare validation; all divergence/regression checks must be clean. | Signed final gate with complete workload, hot-spare, and zero-divergence evidence. | No additional token can replace missing implementation, elapsed observation, or owner decisions. | Yes; cannot pass before deployment and drills